| STORYTALE Risk Assessment & Contingency Plan Prevention, triggers, and recovery actions for the StoryTale implementation. | IT ELECT 4 3 AUG 2026 John Benedict S. Alejo |
| --- | --- |

# Assessment Approach

Risks are evaluated using qualitative probability and impact levels. High-impact risks receive an explicit prevention action, a measurable warning trigger, and a contingency that protects the core local reading experience.

| 10 tracked risks | 7 high-impact risks | 3 AI/API risks | Weekly review frequency |
| --- | --- | --- | --- |

# Risk Priority Matrix

| Probability | Medium Impact | High Impact |
| --- | --- | --- |
| High probability | R4, R7 | R3, R6 |
| Medium probability | - | R1, R2, R5, R8, R9 |
| Low probability | - | R10 |

# Risk Register and Contingencies

| ID | Risk | Prob. | Impact | Prevention / Mitigation | Contingency | Trigger |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Cloud API quota, outage, or slow response | Medium | High | Cache successful results; avoid duplicate calls; add retry and timeout rules. | Keep the last valid result and allow the user to retry later. | API error or quota warning |
| R2 | Gemini story analysis returns inconsistent data | Medium | High | Use strict structured output, validation, stable IDs, and chapter-to-book context. | Reject invalid output and use a safe minimal chapter package. | Schema or continuity check fails |
| R3 | Generated characters or assets change appearance | High | High | Lock reference images, character descriptions, reusable asset IDs, and approved catalogs. | Regenerate only the failed variant or replace it with an approved placeholder. | Identity score or visual review fails |
| R4 | Offline voice packs make the app too large | High | Medium | Limit the first release to five optional, quantized ONNX voice packs. | Ship one default voice and let users download or remove other packs. | Install size exceeds target |
| R5 | Animated Story Mode performs poorly on mobile | Medium | High | Pre-generate assets, cache audio, limit visible sprites, and profile on Android. | Reduce motion, image resolution, and active layers while keeping subtitles and audio. | Dropped frames or high memory use |
| R6 | Different EPUB structures break import or chapters | High | High | Normalize spine and HTML content; test multiple EPUB layouts and encodings. | Show manual chapter review and keep the original EPUB available. | Missing or merged chapters |
| R7 | DeepL character allowance is consumed too quickly | Medium | Medium | Translate per chapter, cache every result, and display usage before a request. | Allow English-only reading until the allowance resets or is upgraded. | Usage reaches 80 percent |
| R8 | Local data or generated assets are lost | Medium | High | Use durable local database and file storage with atomic saves and migrations. | Restore from a local export or rebuild only the affected derived assets. | Missing record after restart |
| R9 | Schedule slips because the scope expands | Medium | High | Protect the MVP, review weekly priorities, and defer music and advanced polish. | Freeze new features and complete the reader, translation, audio, and one chapter demo. | A milestone misses its week |
| R10 | Copyright, privacy, or API key exposure | Low | High | Use user-owned or public-domain EPUBs, local files, and server-side secrets. | Remove exposed credentials, rotate keys, and disable affected generated content. | Secret scan or content complaint |

# Response Rules

Stop or isolate any change that threatens book data, API keys, or the ability to read an imported EPUB.

Prefer a smaller working mode over a visually richer mode that crashes or blocks the reader.

Record the trigger, decision, owner, and outcome in the weekly progress notes.

Escalate any high-impact risk that remains open for two consecutive weekly reviews.

Reassess probability and impact after mitigation is implemented.

# Ownership and Review

The student developer owns the register and reviews it every week. Technical risks are checked during implementation and targeted validation; schedule and scope risks are checked against the Gantt chart. Any activated contingency becomes the next priority until the core StoryTale reading flow is stable again.